## Composite Scores
FY25-013 Biosolids Removal Evaluation | Denali | Merrell Bros | Hodges Farms | TerraGenesis
Price | 9.33 | 2.97 | 4.58 | 10
Project Narrative | 10 | 7 | 5 | 9.5
Quality/Adherance to Specs in Bid Docs | 9.5 | 9.5 | 7.5 | 9.5
Maintenance/Service | 9 | 8 | 6.5 | 9
Delivery/Completion Timeline | 6.5 | 7.5 | 6 | 7
Guarantees/Warranties | 7.5 | 8.5 | 7 | 8
Company's Reputation and Financial Status | 9.5 | 9 | 6.5 | 9
Previous Experience w/Similar Equip/Service | 10 | 8.5 | 7 | 10
Total Score | 71.33 | 60.97 | 50.08 | 72
**All categories max score of 10 points**

## Andy's Scores
FY25-013 Biosolids Removal Evaluation | Denali | Merrell Bros | Hodges Farms | TerraGenesis
Price | 9.33 | 2.97 | 4.58 | 10
Project Narrative | 10 | 7 | 5 | 10
Quality/Adherance to Specs in Bid Docs | 10 | 10 | 6 | 10
Maintenance/Service | 8 | 8 | 6 | 8
Delivery/Completion Timeline | 6 | 8 | 5 | 6
Guarantees/Warranties | 7 | 9 | 6 | 8
Company's Reputation/References | 10 | 10 | 6 | 10
Previous Experience w/Similar Equip/Service | 10 | 10 | 7 | 10
Total Score | 70.33 | 64.97 | 45.58 | 72
Comments | Incumbant with lots of previous experience successfully doing this project for the City. Timeline seems fairly short given previous years' timelines (3wks in proposal, roughly 5 wks in previous years). | Not beneficially reusing biosolids. Very high mob/demob fee. Reasonable timeline (9/29 - 11/7, 5wks) that should avoid any risk of ice. | Not many details or anticipated project timeline in narrative. Cannot read the references page, the scan is low quality and cannot be blown up for better viewing. Start date of 11/15 may have ice implications. | Previous experience working with City, good results. Proposal was short but detailed the project process completely. Vague delivery timeline - start some time in October and take approx 16 days. Seems short but proposed extended working hours of 7 days/week, 12 hr days so might be doable.

## Robby's Scores
FY25-013 Biosolids Removal Evaluation | Denali | Merrell Bros | Hodges Farms | TerraGenesis
Price | 9.33 | 2.97 | 4.58 | 10
Project Narrative | 10 | 7 | 5 | 9
Quality/Adherance to Specs in Bid Docs | 9 | 9 | 9 | 9
Maintenance/Service | 10 | 8 | 7 | 10
Delivery/Completion Timeline | 7 | 7 | 7 | 8
Guarantees/Warranties | 8 | 8 | 8 | 8
Company's Reputation and Financial Status | 9 | 8 | 7 | 8
Previous Experience w/Similar Equip/Service | 10 | 7 | 7 | 10
Total Score | 72.33 | 56.97 | 54.58 | 72
Comments | Lowest mob fee, second lowest unit cost. Very familiar with City and this project as they have completed it the last 3-4 years. Question the ambitious start date, given their knowledge of the ditch shut down dates. | Highest mob fee at $118k and highest unit cost. New to Evans and no site visit. | 2nd highest mob fee (but reasonable) and 2nd highest unit cost. Narrative is unclear on where they are getting permitted land for land application. Start date of mid November could have ice impacts. New to Evans but did come for a site visit. | 2nd lowest mob and lowest unit cost. Has done work for the City before, but not this project and no site visit. Narrative did not mention how they were mixing the ponds, I do not want mixing boats in the ponds as they have damaged the liner in the past.

## Bid Tab Comparison
Work Area: | Unit | Quantity (Est) | Denali | Merrell Bros | Hodges Farm | TerraGenesis | High | Low | Variance (High - Low)
Removal and Disposal of Biosolids | Per Dry Ton | 350 | 560 | 1480 | 1127 | 516.367 | 1480 | 516.367 | 963.633
Mobilization and Demobilization | ea. | 1 | 7000 | 118500 | 18750 | 8595 | 118500 | 7000 | 111500
Total Estimated Cost |  |  | 203000 | 636500 | 413200 | 189323.45 | 636500 | 189323.45 | 447176.55
Price Score
Vendor | Variance From Low | % above Low | Rank | Score
Denali | 13676.55 | 7.224% | 2 | 9.3263
Merrell Bros | 447176.55 | 236.2% | 4 | 2.9744
Hodges Farm | 223876.55 | 118.3% | 3 | 4.5819
TerraGenesis | 0 | 0% | 1 | 10
**Score calc=(Max Points)/(1+% Difference from Low Price)**